## Sheet1
| Bi-Weekly Meetings to review data, methodology, and drafts | Revised-Updated edited chapters 1-3 to advisor | Chapter 4 edited final draft to advisor | Chapter 5 edited final draft to advisor | Dissertation final draft to advisor for final round of comments | Dissertation draft to committee | Defense rehearsal | TARGET: Dissertation defense | Post-defense Revision | Submission to Graduate Studies
Plan of Record | 01 Feb - 22 May 2023 | 2023-07-24 | 2023-07-31 | 2023-08-31 | 2023-09-14 | 2023-09-28 | 2023-10-12 | 2023-10-26 | 2023-11-09 | 2023-11-12
Potentially Accelerated Plan | 01 Feb - 09 May 2023 | 2023-07-25 | 2023-08-01 | 2023-08-15 | 2023-08-22 | 2023-08-29 | 2023-05-30 | 2023-06-06 | 2023-06-13 | 2023-06-16
# | Task | 2023-09-14: Amount Completed; 2023-09-28: Effort (days); 2023-10-12: Start date; 2023-10-26: Completion date
-1 | Roll up cash flow statements into a single spreadsheet | 2023-09-14: 2/3; 2023-09-28: 4; 2023-10-12: 2023-06-15; 2023-10-26: 2023-06-19
0 | (a) Record bond data from years 2008-2022 in Data Dashboard. (b) Add debt summaries | 2023-09-14: 15/15 11/11; 2023-09-28: 4; 2023-10-12: 2023-06-19; 2023-10-26: 2023-06-23
1 | Cross-reference Form 990 with financial statements for years 2008-2022 | 2023-09-14: Does not yield useful information.; 2023-09-28: 0; 2023-10-12: 2023-06-23; 2023-10-26: 2023-06-23
2 | Review Related Party Transactions for years 2008-2022 SB740 Grants: 2012-13 - 2021-22 Land & facilities leases: 2022 only | 2023-09-14: Done; 2023-09-28: 3; 2023-10-12: 2023-06-23; 2023-10-26: 2023-06-26
3 | Find and record all bond prospectuses. | 2023-09-14: 4/10; 2023-09-28: 2; 2023-10-12: 2023-06-26; 2023-10-26: 2023-06-28
4 | Cross-reference years 2008-2022 of board meeting data with financial statements. | 2023-09-28: 4; 2023-10-12: 2023-06-28; 2023-10-26: 2023-07-02
5 | Research and characterize types of bonds: conduit bonds, NMTC, loans, forgiven loans | 2023-09-14: 80%; 2023-09-28: 1; 2023-10-12: 2023-07-02; 2023-10-26: 2023-07-03
6 | Research and then cross-reference venture funds with financial statements | 2023-09-28: 4; 2023-10-12: 2023-07-03; 2023-10-26: 2023-07-07
7 | Review & incorporate relevant data from StopRocketship, EduResearcher, & ScoopIt, and HBS & GBS case studies | 2023-09-28: 3; 2023-10-12: 2023-07-07; 2023-10-26: 2023-07-10
8 | Record in Data Dashboard grants and donations. | 2023-09-14: 100%; 2023-09-28: 1; 2023-10-12: 2023-07-10; 2023-10-26: 2023-07-11
9 | Review and cross-reference petitions and renewals with financial statements. | 2023-09-28: 4; 2023-10-12: 2023-07-11; 2023-10-26: 2023-07-15
10 | Review and cross-reference leases with financial statements. | 2023-09-28: 3; 2023-10-12: 2023-07-15; 2023-10-26: 2023-07-18
9 | Submit Chapters 1- 3 draft | 2023-09-28: 7; 2023-10-12: 2023-07-18; 2023-10-26: 2023-07-25
10 | Submit Chapter 4 draft | 2023-09-28: 7; 2023-10-12: 2023-07-25; 2023-10-26: 2023-08-01
11 | Submit Chapter 5 draft | 2023-09-28: 14; 2023-10-12: 2023-08-01; 2023-10-26: 2023-08-15
12 | Dissertation final to advisor | 2023-09-28: 7; 2023-10-12: 2023-08-15; 2023-10-26: 2023-08-22
13 | Submit dissertation to committee | 2023-09-28: 7; 2023-10-12: 2023-08-22; 2023-10-26: 2023-08-29
14 | Defense rehearsal | 2023-09-28: 7; 2023-10-12: 2023-08-29; 2023-10-26: 2023-09-05
15 | Defend! | 2023-09-28: 7; 2023-10-12: 2023-09-05; 2023-10-26: 2023-09-12
16 | Post-defense revision | 2023-09-28: 7; 2023-10-12: 2023-09-12; 2023-10-26: 2023-09-19
17 | Submit dissertation to Graduate Studies | 2023-09-28: 4; 2023-10-12: 2023-09-19; 2023-10-26: 2023-09-23
Notes
1 | Dates in bold are meetings with Roxana